Layer 1 Adoption Readiness

Current state, required fixes and next-week controlled pilot plan

Audience: Agent-standard maintainers, engineering platform, security and pilot owners

Assessment date: August 30, 2026

Target: Begin a controlled adoption effort during the week of August 31, 2026

Status: Conditional go after Priority 0 release gates are satisfied

Decision: Layer 1 has a substantial technical foundation and can support a limited, closely owned pilot next week. It should not be presented as a stable enterprise-wide release until the immutable release, policy boundary, organization wrapper and adoption-safety gates below are complete.

# Terminology boundary

In the six-layer architecture, Layer 1 means the enterprise baseline: the minimum organization-wide operating and control contract. This is different from the repository's AS-1 conformance level, which specifically describes canonical agent instructions and generated client entry points. The pilot should use these terms consistently.

# Current readiness summary

| Capability | State | Assessment |
| --- | --- | --- |
| Canonical operating instructions | Green | One .ruler source fans out to tracked agent entry points. |
| Deterministic quality and supply-chain controls | Green | Doctor, verification, DoD and SBOM checks are implemented and tested. |
| Provider-neutral core | Green | GitHub and Azure DevOps behavior is isolated behind adapters. |
| Configuration and profile contract | Green | Copier exposes supported stacks, architecture, workflow, provider and gate choices. |
| Immutable release distribution | Amber | The project is private/pre-release and currently defaults to mutable HEAD. |
| Organization policy wrapper | Amber | Owners are supplied, but approved tools, data policy and support contacts are not packaged. |
| Existing agent-rule adoption safety | Amber | Preservation is not proven for existing AGENTS.md, CLAUDE.md or .ruler content. |
| Machine-readable control evidence | Amber | Control IDs exist, but results are not yet emitted as a complete evidence record. |

# What is ready today

- A clear operating loop and definition of done for agents working in participating repositories.

- A manifest and schema that declare the selected project, governance, workflow, quality and supply-chain contract.

- Strict local and CI verification, structured no-test waivers, and current CycloneDX or SPDX dependency evidence.

- Version-pinned bootstrap dependencies, SHA-pinned GitHub Actions, and immutable Azure central-template support.

- Transactional staging, dry-run plans, rollback backups and fail-closed package-manager checks.

- A full render matrix covering supported stacks, modes, providers and Azure pipeline variants.

## Pilot value enabled by the foundation

| Value area | Capability available for the pilot |
| --- | --- |
| Security assurance | Pinned external dependencies and current SBOM evidence provide a reviewable software-supply-chain baseline. |
| Quality assurance | Doctor, verification and definition-of-done checks give teams one repeatable completion path. |
| Delivery efficiency | Configurable rendering, dry-run planning, transactional apply and rollback reduce setup and recovery effort. |
| Portfolio governance | A shared manifest, control vocabulary and provider adapters make repository outcomes easier to compare. |

Pilot use: Use these capabilities as the technical foundation; the Priority 0 gates on the following page establish the release, policy and adoption safeguards required before installation.

# Priority 0 fixes required before pilot installation

These are release gates. If any gate is incomplete, the next-week activity should remain assessment and dry-run only.

| ID | Required fix | Deliverable | Acceptance test |
| --- | --- | --- | --- |
| P0-1 | Publish an immutable pilot release | Replace private placeholder versioning and mutable HEAD guidance with a reviewed tag or full commit. Pin installer examples to that revision. | A clean repository can install the exact release twice and produce identical governed outputs. |
| P0-2 | Define the Layer 1 control contract | Publish the baseline controls with owner, intent, enforcement source, evidence, applicability and waivability. Separate mandatory controls from advisory guidance. | Every Layer 1 claim maps to a control ID and a named evidence source. |
| P0-3 | Create the organization pilot wrapper | Supply approved agent clients, AI/data-handling policy link, owner aliases, support/escalation route, approved registries and pilot defaults outside the public provider-neutral template. | Pilot teams receive one approved command and one accountable support path. |
| P0-4 | Protect existing agent instructions | Detect existing AGENTS.md, CLAUDE.md and .ruler files before Ruler runs. Stop and produce a migration report instead of replacing unclassified instructions. | A fixture with existing agent rules is preserved and the installer fails safely with an actionable report. |
| P0-5 | Remove silent architecture selection in adoption | Require an explicit architecture choice for existing repositories until assessment can determine it reliably. | Adoption without an architecture decision cannot proceed beyond dry-run. |
| P0-6 | Publish pilot eligibility and exclusions | State supported stacks, package managers, providers, repository conditions and out-of-scope data or deployment scenarios. | A repository owner can determine eligibility before invoking the installer. |
| P0-7 | Prove release and rollback | Run source tests, all renders, update round trips and dry-run/install/rollback exercises against the immutable release. Capture the results in a release evidence note. | The evidence package records passing checks, known limitations and a tested recovery procedure. |
| P0-8 | Set truthful conformance language | Keep pilot repositories in adopting or pending-remote until authorized remote controls are applied and audited. Do not equate local success with conformance. | Pilot communications and manifests use the same state definitions. |
| P0-9 | Establish pilot operations | Name the release owner, security reviewer, support channel, repository owners, change window, rollback authority and issue triage process. | Every pilot repository has named accountable contacts before installation. |

# Layer 1 control boundary to publish

| Control family | Minimum outcome | Evidence | Policy class |
| --- | --- | --- | --- |
| Instruction governance | One canonical tracked source; generated client outputs; declared supported clients. | AS-AGENT-001, doctor, source/render tests | Protected |
| Ownership and authorization | Named owners for protected paths; no remote mutation without explicit authorization. | Manifest, CODEOWNERS/adapter contract, runbooks | Protected |
| Quality verification | One complete verification command; source changes require recognized tests or an approved exception. | AS-QUAL-001/002, DoD, CI | Test rule waivable |
| Documentation lifecycle | Governed documents carry ownership, status, freshness and valid links. | AS-DOC-001, doctor | Configurable scope |
| Supply-chain integrity | Locked installs, committed current SBOM and immutable external workflow references. | AS-SUPPLY-001/002 | Protected for strict pilot |
| Security baseline | No secrets in source; approved scanning and dependency review; explicit trust boundaries. | Security policy and provider adapter | Protected |
| Conformance truthfulness | Local, remote and target state remain separate and auditable. | Manifest state and authorized audit | Non-waivable |
| Change ownership | Standard updates are reviewed, verified and committed as one coherent change. | Copier update workflow and runbook | Protected |

Policy boundary: Repository instructions may add domain context or stricter requirements, but they must not silently weaken protected Layer 1 controls. Semantic precedence becomes a later-layer capability; the pilot should enforce this boundary through review and deterministic gates.

# Organization pilot wrapper

The public template is intentionally provider-neutral and should remain so. Enterprise-specific requirements belong in a thin private distribution or approved pilot configuration that supplies:

- Approved agent clients and account/licensing expectations.

- Data classification, prohibited-input and AI acceptable-use policy references.

- Portable owner aliases resolved to real GitHub or Azure identities.

- Internal package registries, approved dependency sources and support contacts.

- Pilot defaults, repository eligibility rules and escalation procedures.

# Next-week controlled pilot plan

| Date | Milestone | Required outcome |
| --- | --- | --- |
| Mon, Aug 31 | Freeze scope and ownership | Approve Layer 1 controls, pilot eligibility, responsible owners and conformance language. |
| Tue, Sep 1 | Complete release safeguards | Implement immutable versioning, existing-rule detection and explicit adoption architecture. |
| Wed, Sep 2 | Package organization defaults | Finalize the pilot wrapper, support route, data-policy references and release evidence. |
| Thu, Sep 3 | Dry-run representative repositories | Use at least one greenfield and two existing repositories; review file plans and migration findings. |
| Fri, Sep 4 | Release and begin limited adoption | Tag the approved release, onboard named pilot owners and install only in repositories that passed dry-run review. |

# Pilot acceptance criteria

- The installer uses an immutable agent-standard release and version-pinned bootstrap tools.

- Each repository has a clean worktree, named owner, supported toolchain and approved architecture decision.

- Existing agent instructions are either absent or covered by a reviewed migration plan.

- Dry-run output has been reviewed before any destination changes are applied.

- The manifest verification command and selected SBOM check pass after installation.

- No repository is described as conformant until provider controls are authorized and audited.

- Rollback is tested or rehearsed, and the support owner is available during the change window.

- Pilot metrics and findings are captured without collecting proprietary source or prompt content.

# Pilot measures

| Measure | Definition |
| --- | --- |
| Adoption effort | Elapsed engineering time from approved dry-run to verified commit. |
| First-pass success | Percentage of repositories passing verification without remediation. |
| Change footprint | Files created, merged, preserved and requiring manual attention. |
| Safety | Installation failures, rollbacks, lost configuration or unexpected overwrites. |
| Quality | Verification findings and defects attributable to the standard. |
| Experience | Repository-owner confidence, support demand and clarity of generated guidance. |

# Priority 1 improvements during the pilot

- Emit first-class machine-readable control results rather than relying only on console output.

- Add a read-only GitHub remote auditor to match the Azure DevOps evidence path.

- Introduce a formal repository-rule overlay and precedence contract before broad adoption.

- Create an agent-standard assess report for commands, test locations, architecture indicators and existing agent configuration.

- Expand the exception schema beyond no-test waivers only after controls are classified as configurable, waivable or non-waivable.

- Publish compatibility and migration guarantees for Copier updates before declaring v1.0 stability.

# Go / no-go rule

Go: Begin a limited pilot only when every Priority 0 acceptance test is satisfied and each pilot repository has passed reviewed dry-run assessment.

No-go: If immutable release, existing-rule protection, organization policy ownership or rollback evidence is incomplete, limit next week's activity to assessment and dry runs.

# Repository evidence reviewed

- AGENTS.md - source-repository maintainer contract.

- README.md - product boundary, setup path, verification and pre-release status.

- copier.yml and docs/configuration.md - public configuration API and defaults.

- docs/architecture.md, docs/conformance.md and docs/runbook.md - ownership, controls, states and operating procedures.

- docs/roadmap.md - organization distribution and evidence roadmap.

- template/.ruler/00-operating.md.jinja - canonical generated operating baseline.

- template/.agent-standard/scripts/ - doctor, verification, DoD, merge, skill-sync and SBOM enforcement.

- bin/agent-standard.mjs - detection, staging, dry-run, apply and rollback behavior.

- test/, scripts/verify-source.mjs and scripts/verify-render.ps1 - automated source and rendered-project evidence.

- package.json and CHANGELOG.md - current unpublished release state.